## NEBA Audit Checklist
NEBA TOKEN - Task list for creating a smart contract and auditing it
PHASE 1A
cc
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Basic | 1.2 Token symbol: "$NEBA" | P1 | The symbol is correctly set and indexed by the scanner. | Stock symbol (ticker) for short writing.
Basic | 1.3 Decimals: 18 | P1 | decimals() returns 18. | Number of decimal places; 18 is the standard for ERC-20.
Supply | 1.4 Total supply: fixed at 1,000,000,000 (unchangeable) | P0 | totalSupply() = 1e9*1e18; no ways to increase. | Fixed maximum of 1 billion – cannot be increased.
Supply | 1.5 Minting at initialize() to Treasury Safe | P0 | Transfer(address(0), Treasury, amount) is issued at init; the address is Gnosis Safe. | Initial minting at initialize() and transfer to treasury for control and accountability.
Supply | 1.6 No public mint()/burn() | P0 | There are no public/external mint/burn in ABI; tests confirm this. | Users/admin cannot change supply via public functions.
Allocation | 1.7 On-chain distribution 60% Investors / 40% Treasury | P1 | The genesis script sends the exact amounts; events are valid. | On-chain allocation for transparency and traceability.
Fund security | 1.8 Prohibition of confiscation/seizure | P0 | No functions for seizing foreign balances; invariant tests. | Admin functions do not allow seizure of balances from addresses.
SECTION 2: ARCHITECTURE, STANDARDS, AND UPGRADABILITY
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Technologies | 2.2 Solidity ^0.8.20 | P0 | pragma and solc in CI match; build passes. | Minimum version of Solidity with built-in protections.
Technologies | 2.3 OpenZeppelin Upgradeable (pinned) | P0 | package-lock/foundry remappings pinned; license ok. | Standardized libraries with pinned versions for security and reproducibility.
Standards | 2.4 ERC-20 compatibility | P0 | Interfaces and Transfer/Approval events according to standard; tests pass. | Compatibility with mandatory ERC-20 functions and events.
Upgradability | 2.5 UUPS (EIP-1822) | P0 | Proxy triggered; ProxyAdmin/Safe controls. | UUPS proxy for flexible and controllable upgrades.
Upgradability | 2.6 _authorizeUpgrade only for UPGRADER_ROLE | P0 | Role is set to Safe; test for unauthorized denial. | Only authorized addresses can approve new implementations.
Upgradability | 2.7 Storage Gap __gap | P0 | Available spare slots; layout snapshot. | Reserved storage slots for future fields without breaking the layout.
Inheritance | 2.8 ERC20Upgradeable, Pausable, AccessControl, ERC20Permit, UUPS, ReentrancyGuard | P1 | Contract compiles; lint and tests pass. | Required mixins for functions, security, and upgradeability.
SECTION 3: ACCESS CONTROL AND MANAGEMENT
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Roles (critical) | 3.2 UPGRADER_ROLE to Safe | P0 | Grant event; deny foreign addresses. | Control over upgrades is under multisig.
Roles (critical) | 3.3 PARAM_MANAGER_ROLE to Safe (commit→reveal) | P1 | Two-step flow works; logs available. | Sensitive parameters are changed through a two-step process.
Roles (critical) | 3.4 FINANCE_ROLE to Treasury Safe | P0 | Only Treasury Safe can withdraw/direct proceeds. | Manages funds from sales under the control of Treasury Safe.
Roles (management) | 3.5 BLOCKLIST_MANAGER_ROLE | P1 | Can add/remove addresses; events issued. | Role for administering blocked addresses.
Roles (management) | 3.6 WHITELIST_MANAGER_ROLE | P1 | Can maintain allowlist; logs available. | Role for administering the allowlist.
Roles (delegable) | 3.7 SNAPSHOTTER_ROLE | P2 | snapshot() only works with role; events checked. | Allows snapshots of state for distribution/audit.
Pause roles | 3.8 GOVERNANCE_UNPAUSER_ROLE (unpause only) | P0 | Only this role can unpause. Must go through Timelock (see Phase 1B). | Controlled recovery after pause, requiring publicity and delay.
Pause roles | 3.9 EMERGENCY_GUARDIAN_ROLE (pause only, immediate) | P0 | Can call pause() immediately (without Timelock); unpause denied. Also includes BOT_PAUSER functionality. | Critical role for immediate response to incidents. Held by Security Council or Bot.
SECTION 4: SECURITY AND EMERGENCY MECHANISMS
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Pausable | 4.2 Transfers only whenNotPaused | P0 | Transfers revert on pause; tests correct. | Transfers stop during emergency pause.
Pausable | 4.3 approve/permit also work during pause | P1 | Functions are not gated by whenNotPaused. | Allows pre-configuration/rotations during an incident.
Pausable | 4.4 pause() for EMERGENCY_GUARDIAN (immediate) | P0 | The role can pause immediately; events are emitted. | Security subjects can activate an immediate stop.
Pausable | 4.5 unpause() only for GOVERNANCE_UNPAUSER_ROLE | P0 | unpause from other addresses (including EMERGENCY_GUARDIAN) reverts. | Controlled recovery after an incident.
Pausable | 4.6 Auto-pause activated on-chain via Circuit Breakers | P1 | Auto-pause is triggered on-chain under the conditions in Section 17. | Automated on-chain protection in case of anomalies.
Events | 4.7 All admin actions emit events | P1 | Event coverage; indexed fields. | Full traceability for auditing and monitoring.
SECTION 5: TESTING AND VERIFICATION
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Neg Tests | 5.2 Reverts/access/pause/boundaries | P0 | Negative tests pass; described cases. | Cover incorrect inputs and prohibited actions.
Integration | 5.3 Upgrade flow | P0 | E2E test includes deployment→upgrade (with 48-hour delay)→validation. | Real user/admin flow is tested.
Fuzz | 5.4 All external/public (Fuzzing) | P0 | Fuzz tests without critical failures. | Critical for detecting unexpected paths in a complex system (High Priority).
Invariants | 5.5 /test/invariants (Invariant tests) | P0 | Invariant tests pass consistently. | Critical for formalized properties that must always hold (High Priority).
Invariants | 5.6 Cap/balances match | P0 | Sum of balances == totalSupply. | Accounting consistency of the token.
Invariants | 5.7 BL blocks; pause stops mutations | P0 | Tests cover failures during BL/pause. | Proves the effectiveness of controls.
Static analysis | 5.8 Slither configured | P1 | slither.config.json in the repo; no critical issues. | Automatic vulnerability analysis.
Report | 5.9 Triage in /audits/slither.md | P2 | Report with High/Medium addressed. | Documented solutions/risk acceptance.
Formal analysis | 5.10 SMTChecker for critical | P2 | Compilation with SMT included without errors. | Additional formal verification.
Upgrade test | 5.11 Layout validation (Automated in CI) | P0 | Comparison of storage layout before/after. CI must block merging in case of inconsistency. | Does not allow slot incompatibility that would corrupt data.
Upgrade test | 5.12 UUPS/rollback/init-guard (Initialization protection) | P0 | Coverage of proxiableUUID/rollback. The implementation must use _disableInitializers(). | Protection against logical contract takeover through direct initialization.
Matrices | 5.13 EOA + Safe scenarios | P1 | Admin operations from Safe pass. | Real admin/operator paths are covered.
Matrices | 5.14 L2 forks stateful | P2 | Fork tests on Base Sepolia. | Tests against target L2 network behavior.
Matrices | 5.15 Failure injection | P2 | Mock/forced errors covered. | Simulations of errors/temporary failures.
Matrices | 5.16 Load/DoS | P2 | Tests with a large number of addresses/tags. | Limits for multiple participants and high volumes.
SECTION 6: DOCUMENTATION AND CODE QUALITY
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
NatSpec | 6.2 Export to /docs/natspec.md | P2 | File generated by build. | Documentation for external integrators.
README | 6.3 Overview/diagram/instructions/changelog | P2 | README covers all sections. | Quick start and operational instructions.
Factsheet | 6.4 LOC/solc/optimizer/networks/dependencies | P2 | Audit Factsheet section available. | Facts for auditors in one section.
Threat model | 6.5 /audits/threat-model.md | P2 | Assets/risks/controls described. | Assets, adversaries, and controls identified.
Complexity notes | 6.6 Notes per contract | P2 | List in README. | Helps with review and risk acceptance.
Coding std | 6.7 CEI model | P0 | All external calls after effects. | Orders side effects against reentries.
Coding std | 6.8 Custom errors + events | P1 | Replaced string reverts; events for critical ones. | Cheaper than strings; better telemetry.
Coding std | 6.9 No tx.origin | P0 | Static analysis confirms. | Avoids anti-pattern for auth.
Coding std | 6.10 No delegatecall to untrusted | P0 | No such sections; failure tests. | Reduces the risk of context hijacking.
Coding std | 6.11 No block.timestamp for randomness | P1 | Not used as random; if yes—VRF. | Not used as a source of randomness.
Coding std | 6.12 External calls validate return | P1 | All call/ERC20 transfers with SafeERC20. | Catches silent failures and failures.
SECTION 7: STORAGE, ENVIRONMENT, AND CI/CD
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Hygiene | 7.2 No dead code/unused imports | P1 | Lint/CI cleans. | Reduced surface area and confusion.
Dependencies | 7.3 Pinned versions | P1 | Lockfiles committed. | Reproducible builds.
Environment | 7.4 Foundry or Hardhat | P1 | forge/hardhat commands work. | Build/test/deploy tools.
Environment | 7.5 Fixed solc; --via-ir and runs documented | P1 | Config in foundry.toml/hardhat.config. | Control over compiler and optimizations.
Environment | 7.6 .env.example without secrets | P0 | No keys in git; secrets via vault. | Secrets are kept outside the repo.
Build | 7.7 Deterministic builds | P1 | Same inputs → same bytecode (snapshot). | Same inputs → same bytecode.
Build | 7.8 forge build single command | P1 | The command works locally/CI. | Easy to start for auditors/CI.
SECTION 8: OPERATIONAL READINESS AND AUDIT
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Verification | 8.2 forge/hardhat verify | P1 | Contracts verified after deployment. | Public code and metadata.
Addresses | 8.3 /audits/addresses.json | P1 | All addresses filled in; PR reviewed. | A single source of truth for addresses.
Gas | 8.4 forge snapshot with budgets | P2 | File with gas metrics/targets. | Control over costs.
Gas | 8.5 No unbounded loops | P0 | Static analysis + tests confirm. | Prevents DoS/expensive gas.
Ops | 8.6 Runbooks for pause/upgrade/incidents | P1 | Documents in /audits/runbooks/*. | Described steps in case of problems.
Git | 8.7 Audit branch audit/neba-v1 | P2 | Branch created; no force-push. | Stable base for audit.
Git | 8.8 Commit hash provided | P2 | Hash sent to Hacken. | The auditor reproduces the version exactly.
Git | 8.9 Signed tag git tag -s | P2 | Signature verified. | Cryptographic authentication of the release.
Checklist | 8.10 One-step setup works | P1 | clone→install→build→test passes cleanly. | Guarantees a working project out-of-the-box.
Diagram | 8.11 PDF architecture diagram | P3 | File in /audits/architecture.pdf. | Visual diagram for auditors/investors.
Subcategory | Requirement | Priority | Acceptance criteria / Notes | Explanation
PHASE 1B
SECTION 9: ADDITIONAL SECURITY REQUIREMENTS
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Roles | 9.2 DEFAULT_ADMIN/UPGRADER/GOVERNANCE_UNPAUSER to Timelock | P0 | These roles are owned by Timelock. EMERGENCY_GUARDIAN is NOT to Timelock. | Admin power goes through timelock, but emergency pause bypasses it.
Safe roles | 9.3 Safe PROPOSER/CANCELLER in Timelock | P1 | Safe can propose/cancel operations. | Safe proposes/cancels queue-based transactions in timelock.
Deployer | 9.4 Renounce DEFAULT_ADMIN from the deployer | P0 | EOA (the address used for deployment) no longer has admin rights. | Removes single-point-of-failure of EOA.
Checks | 9.5 48-hour validation/roles | P1 | Simulation schedule→execute after 48 hours. | Checks that the governance flow is active.
Emergency | 9.6 Pause via EMERGENCY_GUARDIAN_ROLE (immediate) or Circuit Breaker (automatic) | P0 | Both paths work; logs. Unpause goes ONLY through Timelock (12.2). | Quick response paths available (manual and automatic).
Upgrade flow | 9.7 schedule→48h→execute | P0 | Sample upgrade successfully passed through the full cycle. | Transparent process with response time.
UUPS Proxy | 9.8 Deploy and init | P0 | Proxy+implementation addresses published. | UUPS token behind proxy.
ENV | 9.9 Secrets outside the repo | P0 | ENV from vault; .env.example without keys. | Reduces key leaks.
Tests | 9.10 Local+CI pass | P1 | GitHub Actions green. | Reliability of build/test pipeline.
Slither | 9.11 High/Medium fixed | P1 | Report in /audits/slither.md. | Clean result for critical/medium findings.
Echidna | 9.12 Pause/upgrade invariants | P1 | Tests stable ≥N runs. | Formal verification of key properties.
Monitoring | 9.13 Role/pause/upgrade alarms | P1 | Off-chain alarms in config. | 24/7 monitoring of critical events.
Artifacts | 9.14 Audit package ready | P2 | Scope, models, dependencies, addresses. | External audit kit.
Publication | 9.15 Proxy/impl/timelock/safe table | P2 | Markdown/CSV published. | Public transparency after deployment.
Multisig | 9.16 3-of-5 (Main), 2-of-3 (Security/Operational), hardware wallets | P0 | All owners configured. | Reduction of key compromise risks.
Owner | 9.17 Safe/Timelock is owner/admin where necessary | P0 | transferOwnership/roles to the correct entities (Safe or Timelock). | Centralization of admin rights under multisig/timelock.
HSM | 9.18 Operational keys in Vault/HSM | P1 | Access via MPC/HSM. | Secure key storage/rotation.
AccessControl | 9.19 Separate roles for critical actions | P0 | Least-privilege enforced. | Minimum necessary rights.
Policy | 9.20 Immutable or UUPS in README | P2 | Documented decision (UUPS). | Clarity for future changes.
Limits | 9.21 Daily limits from Treasury/bridges | P1 | Safe spending limits active. | Damage limitation in case of compromise.
Oracles | 9.22 Chainlink freshness checks | P1 | Stale/threshold protections implemented. | Fail-closed in case of price feed issues.
SWC | 9.23 SWC test coverage | P2 | Test matrix→SWC. | Coverage of known vulnerability classes.
Forta | 9.24 Anomaly bots | P2 | Alarms active. | Early detection of risky events.
OpSec | 9.25 2FA/devices/recovery | P1 | Checklist signed. | Reduces operational risks.
Incidents | 9.26 Playbook for pause/communication | P1 | Document approved; dry-run. | Quick coordination in case of an incident.
Cross-chain | 9.27 No own bridge; if there is one—limits | P1 | Policy documented. | Avoids high-risk bridges/controls.
Bug Bounty | 9.28 Immunefi program | P2 | Pages/rules public. | Encourages external researchers to report.
PHASE 2
SECTION 10: Governance and Treasury (Core)
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Buyback | 10.2 Hooks off by default | P2 | Features exist but are disabled. | Preparedness for future policies without risk now.
Multisig | 10.3 3-of-5 for critical disbursements | P0 | Policy in Safe; testing. | Increased security for outflows.
Commit-Reveal | 10.4 Sensitive parameters | P1 | Full commit→reveal flow in tests. | Reduces manipulation/MEV during changes.
Reserve | 10.5 Reserve/Rebalance Policies | P2 | Documented rules. | Stabilization of treasury and liquidity.
Automation | 10.6 Automatic transfers | P2 | Tasks are configured. | Operational efficiency with limits/alarms.
SECTION 11: Vesting and TGE
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Claims | 11.2 Pull-based claims | P0 | No mass transfers; reentrancy guard. | Reduces reentrancy/DoS risks.
Exceptions | 11.3 Override after timelock | P1 | Process and events documented. | Transparent exceptions with deferral.
SECTION 12: Sales and Crowdfunding
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Controls | 12.2 Pause/finalize/report | P1 | Admin operations working; logs. | Operational controls on sales.
Treasury | 12.3 Withdraw to Treasury Safe | P0 | Only Treasury Safe receives the funds. | Secure movement of funds.
Refunds | 12.4 Refund at Soft Cap | P1 | Refund options are active. | Protection of participants.
Merkle | 12.5 New roots; exceptions | P1 | Admin functions working; immutability for old ones. | Flexible addition of tranches/participants.
Immutability | 12.6 Past roots immutable | P0 | State/events prohibit change. | Guarantee against retroactive manipulation.
SECTION 13: Advanced Circuit Breakers
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Reset | 13.2 Min. 30m freeze + MANDATORY MANUAL reset | P0 | Timers/events valid. After 30 min, the system remains stopped until manually restarted (via GOVERNANCE_UNPAUSER_ROLE). | Limited restriction time, but requires manual intervention and governance process for recovery.
Response | 13.3 Warning→Restricted→Halt (Auto-Pause) | P1 | States and transitions covered. | Escalation according to risk.
Oracle deviation | 13.4 Chainlink/TWAP deviation | P1 | Automatic pause in case of large deviations. | Pause during atypical price movements.
SECTION 14: Market Controls
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Initial limits | 14.2 maxTxBps/maxWalletBps/cooldown | P1 | Parameters are working; failure tests. | Initial anti-bot restrictions.
Exemptions | 14.3 Allowlist exemptions | P1 | List enforced; logs. | Operational addresses/partners without limits.
Same-block | 14.4 Back-to-back ban | P1 | Tests block two operations in one block. | Prevents same-block arbitrage.
Gas/Router | 14.5 Gas limits; allowlisted routers | P2 | Policies are enforced. | Control of DEX routes and gas abuse.
Deactivation (Gas) | 14.6 Function for complete deactivation of controls (P18) and Circuit Breakers (P17) | P1 | PARAM_MANAGER can disable all these checks with a single transaction. | Reduction of gas costs after market stabilization.
SECTION 15: Oracles and Pricing
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
SECTION 16: Compliance and Regulations
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Hooks | 16.2 WL/BL in _update (or _beforeTokenTransfer) | P1 | Before transfer, allow/deny is validated. | On-chain verification of allow/deny before transfer.
SECTION 17: Interfaces and UX
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Snapshot | 17.2 snapshot() for distributions | P2 | Event Snapshot; access via SNAPSHOTTER_ROLE. | Sealing state for fair distributions.
SECTION 18: NextBasket NFT Pool
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
PoR | 18.2 ERP→Hash→IPFS on-chain | P2 | Hash and CID recorded; verifiable. | Cryptographic proof of revenue.
Stabilization | 18.3 7% rule; USDC vault | P2 | Rules encoded; verifiable. | Reserve for stability and liquidity.
Compound | 18.4 USDC→NEBA swap + restake (MEV/Slippage Protection) | P1 | Simulations/risk limits. Mandatory strict slippage controls and protection against sandwich attacks. | Automatic capitalization of rewards with protections against market manipulation.
dNFT | 18.5 Dynamic NFT receipts | P2 | Meta-data updatable; tests. | On-chain proof of participation/rights.
SECTION 19: Infrastructure and Automation
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Monitoring | 19.2 24/7 alerts | P1 | Alarms for key events active. | Operational visibility and response.
Fidesium | 19.3 Continuous audit + audit NFTs | P3 | Integration activated. | Continuous verification and provable traces.
SECTION 20: Audits and Bug Bounty
Subcategory | Requirement | Priority | Acceptance Criteria | Explanation
Formal | 20.2 Slither/Echidna/Manticore | P1 | Tools configured/launched. | Combination of static/dynamic/formal techniques.
Bug Bounty | 20.3 Immunefi program | P2 | Rules/levels public; link in README. | Incentives for discovering and reporting vulnerabilities.